## Slide 2: sheSecure
Project Overview
A women safety app with the aim to increase safety and security to women of all age and for empowering women by using technology as a social tool
Page 3
Notes: Illustration:
- https://www.freepik.com/free-vector/couple-riding-supermarket-shopping-cart_2238492.htm

## Slide 3
Page
ACTIVITIES | DETAILED ACTIVITIES | ALLOTED WEEKS
Proposal & Planning | Extensive Research on various aspects of women safety and Security Analyzing existing Solution Understanding user needs ,gathering data on safety statistics Outlining project scope and setting objectives | 0-1 0-1 1-3 3-4
Analysis & Design | Evaluation on costs ,market demand for financial feasibility Evaluation on technology stack Creating system architecture, database scheme and functionality A detailed project plan with timelines | 4-5 5-6 5-6
Skill Development | Acquiring knowledge for Twilio API,JAVA Learning Android Studio for mobile app development Understanding MONGODB for data storage | 6-8
Implementation | Building the mobile Application Testing and Debugging the entire app Development on testing environment Final Deployment in the market | 8-13 13-14 14-15
Notes: Illustration :
https://www.freepik.com/free-vector/teamwork-characters-operator-crew-front-screen-presentations_4997765.htm

## Slide 4
Gantt Chart
Task done
Task duration(week)
Notes: Illustration :
https://www.freepik.com/free-vector/teamwork-characters-operator-crew-front-screen-presentations_4997765.htm

## Slide 5
Page
NODES | ACTIVITIES | WEEKS RECQUIRED | Predecessors
A | Extensive Research | 1 | -
B | Analyzing Existing Solution | 1 | A
C | Understanding & Gathering Data on User Needs | 2 | -
D | Outlining Project Scopes | 1 | B,C
E | Financial Feasibility | 1 | D
F | Evaluation on Technology Stack | 1 | E
G | Creating System Architecture | 1 | F
H | Detailed Plan Project | 1 | D
I | Acquiring Knowledge for APIs | 2 | J
J | Learning Android Studio and work with Emulators | 2 | G,H
K | Learning MongoDB and database handlings | 2 | I
L | Building Mobile Application | 4 | J
M | Testing and Debugging | 2 | L,K
N | Final Deployment | 1 | M
Notes: Illustration :
https://www.freepik.com/free-vector/teamwork-characters-operator-crew-front-screen-presentations_4997765.htm

## Slide 6
Page 8
Pert Diagram
Notes: Illustration:
- https://www.freepik.com/free-vector/couple-riding-supermarket-shopping-cart_2238492.htm

## Slide 7: sheSecure
Fishbone Diagram
Page 8
Quality
Cost
Designing
Testing
Coding
Listening
Insufficient focus on code review
Budget constraint
Inadequate quality assurance
Unforeseen expenses
Scope
Scope creep due to additional features
Unclear project objectives
Compatability
issues
Inadequate user feedback in corporation
Lack of comprehensive test coverage
Replicating real scenarios difficulties
Overly complex convoluted code
Misinterpretation
of user requirements
Inconsistencies in coding standard
Inadequate communication
Time
Unrealistic project timelines
Unexpected delays
Notes: Illustration:
- https://www.freepik.com/free-vector/couple-riding-supermarket-shopping-cart_2238492.htm

## Slide 8: Team KICHU EKTA BANABO
FATEEN NOOR RAFEE
NOWSHIN MAHJABIN
21004128
RIHILA SUMAYYA
Page 17
21004120
210041110
Notes: Illustration :
https://www.freepik.com/free-vector/teamwork-characters-operator-crew-front-screen-presentations_4997765.htm

## Slide 9: Thank You!
Notes: Illustration:
- https://www.freepik.com/free-vector/couple-riding-supermarket-shopping-cart_2238492.htm